## Sheet1
Project Name | Project Manager | Charge Code | Customer | Project Status | Task Name | Planned Start Date | Planned Finish Date | Planned Duration | Planned Hours | Planned Cost | Planned Resource Cost | Percent Complete | Person | Linked From | Linked To | Actual Start Date | Actual Finish Date | Actual Duration | Actual Hours | Actual Cost | Actual Resource Cost | Remaining Hours | Milestone | Complete | Priority | WBS | Locked | Baseline Duration | Baseline Hours | Baseline Start Date | Baseline Finish Date | Baseline Cost | Notes | Summary | Dependency (From) | Dependency (To) | Tags | Board | To Do list
GANTT_projet (seconde version) | James Fender |  |  | Open | Projet | 2023-01-04 | 2023-07-01 | 128 days | 287.25 hours |  |  | 29 |  |  |  | 2023-01-04 | [5 empty] | 287.25 hours | False | False | Medium | 1 | False | [6 empty] | True |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Revue N°1 | 2023-01-11 | 2023-01-11 | 15 minutes | 0.75 hours |  |  | 0 | Nelsone GRAVEAU [33.33%] Loup SONNEVILLE [33.33%] Jean-Rémy DION [33.33%] | [8 empty] | 0.75 hours | False | False | Medium | 1.1 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Revue N°2 | 2023-02-27 | 2023-02-27 | 50 minutes | 2.5 hours |  |  | 0 | Nelsone GRAVEAU [33.33%] Loup SONNEVILLE [33.33%] Jean-Rémy DION [33.33%] | [8 empty] | 2.5 hours | False | False | Medium | 1.2 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Revue N°3 | 2023-05-22 | 2023-05-22 | 50 minutes | 2.5 hours |  |  | 0 | Nelsone GRAVEAU [33.33%] Loup SONNEVILLE [33.33%] Jean-Rémy DION [33.33%] | [8 empty] | 2.5 hours | False | False | Medium | 1.3 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Livraison | 2023-07-01 | 2023-07-01 | 0.88 days | 21 hours |  |  | 0 | Nelsone GRAVEAU [33.33%] Loup SONNEVILLE [33.33%] Jean-Rémy DION [33.33%] | étudiant 1 : Loup SONNEVILLE | [7 empty] | 21 hours | False | False | Medium | 1.4 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | étudiant 1 : Loup SONNEVILLE | 2023-01-04 | 2023-02-15 | 31 days | 168 hours |  |  | 62 |  |  | Livraison | 2023-01-04 | [5 empty] | 168 hours | False | False | Medium | 1.5 | False | [6 empty] | True |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Administrer les recettes test | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Loup SONNEVILLE | [8 empty] | 7 hours | False | False | Medium | 1.5.1 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Consulter l'état de la machine | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Loup SONNEVILLE | [8 empty] | 7 hours | False | False | Medium | 1.5.2 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser le modèle de la BDD du projet | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Loup SONNEVILLE | [8 empty] | 7 hours | False | False | Medium | 1.5.3 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Diagramme GANTT (première version) | 2023-01-04 | 2023-01-12 | 6.13 days | 49 hours |  |  | 100 | Loup SONNEVILLE |  |  | 2023-01-04 | 2023-02-20 | 34 days |  |  |  | 49 hours | False | True | Medium | 1.5.4 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | écrire un rapport sur le choix des différents types de BDD | 2023-01-09 | 2023-01-24 | 10.5 days | 84 hours |  |  | 97 | Loup SONNEVILLE |  |  | 2023-01-09 | [5 empty] | 84 hours | False | False | Medium | 1.5.5 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Gérer la remontée des alarmes 'user' et 'machine' | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Loup SONNEVILLE | [8 empty] | 7 hours | False | False | Medium | 1.5.6 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | BDD reliée à la CPU B&R | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Loup SONNEVILLE | [8 empty] | 7 hours | False | False | Medium | 1.5.7 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | diagramme GANTT (seconde version) | 2023-02-09 | 2023-02-09 | 0.88 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.8 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Choix la Base de données | 2023-01-09 | 2023-01-16 | 5.25 days |  |  |  | 100 |  |  |  | 2023-01-09 | 2023-02-20 | 31 days |  |  |  | 0 Hours | False | True | Medium | 1.5.9 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | rapport LAMP | 2023-01-23 | 2023-01-23 | 0.88 days |  |  |  | 43 |  |  |  | 2023-01-23 | [5 empty] | 0 Hours | False | False | Medium | 1.5.10 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Intallation de LAMP | 2023-01-10 | 2023-01-25 | 10.5 days |  |  |  | 100 |  |  |  | 2023-01-10 | 2023-02-20 | 30 days |  |  |  | 0 Hours | False | True | Medium | 1.5.11 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Rapport MS Project | 2023-02-08 | 2023-02-15 | 5.25 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.12 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Rapport GitHub | 2023-01-17 | 2023-01-25 | 6.13 days |  |  |  | 97 |  |  |  | 2023-01-17 | [5 empty] | 0 Hours | False | False | Medium | 1.5.13 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | installation PHPMyAdmin | 2023-01-18 | 2023-01-24 | 4.38 days |  |  |  | 100 |  |  |  | 2023-01-18 | 2023-02-20 | 24 days |  |  |  | 0 Hours | False | True | Medium | 1.5.14 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Rapport PHPMyAdmin | 2023-01-30 | 2023-02-08 | 7 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.15 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open |  | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.16 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.17 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.18 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.19 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.20 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.21 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.5.22 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | étudiant 2 : Nelson GRAVEAU | 2023-01-04 | 2023-02-27 | 39 days | 42 hours |  |  | 0 | [9 empty] | 42 hours | False | False | Medium | 1.6 | False | [6 empty] | True |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Interpréter les trames CAN pour l'IHM | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Nelsone GRAVEAU | [8 empty] | 7 hours | False | False | Medium | 1.6.1 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser une IHM via le langage structured text | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Nelsone GRAVEAU | [8 empty] | 7 hours | False | False | Medium | 1.6.2 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Gérer les alarmes 'machines' | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Nelsone GRAVEAU | [8 empty] | 7 hours | False | False | Medium | 1.6.3 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Programmer les pages IHM | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Nelsone GRAVEAU | [8 empty] | 7 hours | False | False | Medium | 1.6.4 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser la charte graphique | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Nelsone GRAVEAU | [8 empty] | 7 hours | False | False | Medium | 1.6.5 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Création d'un tableau comparatif de la concurrence du Power Panel 45 | 2023-01-16 | 2023-01-17 | 2 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.6 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Documentation du Power Panel 45 | 2023-01-16 | 2023-01-18 | 3 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.7 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Rapport sur le logiciel automation studio | 2023-01-16 | 2023-01-17 | 2 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.8 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Diagramme de séquence | 2023-01-24 | 2023-01-24 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.9 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Diagramme de séquence de la communication | 2023-01-30 | 2023-01-30 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.10 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser le storyboard de l'IHM | 2023-01-31 | 2023-02-06 | 5 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.11 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | rapport automation studio IHM | 2023-02-06 | 2023-02-06 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.12 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Connection de l'IHM au système | 2023-02-02 | 2023-02-09 | 6 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.13 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Amélioration des rapports | 2023-02-13 | 2023-02-27 | 11 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.14 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Apprentissage d'Automation studio | 2023-02-13 | 2023-02-27 | 11 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.15 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.16 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.17 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.18 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.19 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.20 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | [Nouvelle tâche] | 2023-01-04 | 2023-01-04 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.6.21 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser la base du diaporama de présentation | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Nelsone GRAVEAU | [8 empty] | 7 hours | False | False | Medium | 1.6.22 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | étudiant 3 : Jean-Rémy DION | 2023-01-04 | 2023-07-01 | 112.88 days | 50.5 hours |  |  | 0 | [9 empty] | 50.5 hours | False | False | Medium | 1.7 | False | [6 empty] | True |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Paramétrer l'émulateur | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Jean-Rémy DION | [8 empty] | 7 hours | False | False | Medium | 1.7.1 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser le MOM | 2023-01-09 | 2023-01-09 | 1 hour | 1 hour |  |  | 0 | Jean-Rémy DION | [8 empty] | 1 hour | False | False | Medium | 1.7.2 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser le modèle des LOGBOOKS | 2023-01-09 | 2023-01-09 | 30 minutes | 0.5 hours |  |  | 0 | Jean-Rémy DION | [8 empty] | 0.5 hours | False | False | Medium | 1.7.3 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser la nomenclature | 2023-01-11 | 2023-01-11 | 0.88 days | 7 hours |  |  | 0 | Jean-Rémy DION | [8 empty] | 7 hours | False | False | Medium | 1.7.4 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Décoder les trames CAN | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Jean-Rémy DION | [8 empty] | 7 hours | False | False | Medium | 1.7.5 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Programmer les cycles de fonctionnement de l'émulateur | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Jean-Rémy DION | [8 empty] | 7 hours | False | False | Medium | 1.7.6 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Interpréter les trames CAN, pour l'interface WEB de l'émulateur | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Jean-Rémy DION | [8 empty] | 7 hours | False | False | Medium | 1.7.7 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser une interface WEB [[tactile]] | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Jean-Rémy DION | [8 empty] | 7 hours | False | False | Medium | 1.7.8 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Programmer les pages WEB | 2023-01-04 | 2023-01-04 | 1 day | 7 hours |  |  | 0 | Jean-Rémy DION | [8 empty] | 7 hours | False | False | Medium | 1.7.9 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Présentation de B&R | 2023-01-16 | 2023-01-16 | 0.88 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.7.10 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Rédaction de la nomenclature du système | 2023-01-09 | 2023-01-16 | 5.25 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.7.11 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Rédaction documentation matériel | 2023-01-16 | 2023-01-21 | 5.25 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.7.12 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Comparatifs des matériels avec leur équivalent concurrents | 2023-01-18 | 2023-01-22 | 3.5 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 1.7.13 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser le schéma de câblage | 2023-01-24 | 2023-01-24 | 1 day |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 2 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Documentation sur le BUS CAN | 2023-01-24 | 2023-01-25 | 2 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 3 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Programmation du calculateur | 2023-01-26 | 2023-01-30 | 3 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 4 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Analyse du logiciel Muxtrace | 2023-01-26 | 2023-02-01 | 5 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 5 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Programmation de l'interface WEB | 2023-01-31 | 2023-02-27 | 20 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 6 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Test de la maquette | 2023-01-30 | 2023-01-31 | 2 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 7 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Rapport automation studio mobile | 2023-01-31 | 2023-02-23 | 18 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 8 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Prise en main de l'ancienne l'interface WEB | 2023-02-02 | 2023-02-09 | 6 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 9 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Amélioration du storyboard | 2023-02-09 | 2023-02-15 | 5 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 10 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Explication du fonctionnement du FT50 | 2023-02-13 | 2023-02-15 | 3 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 11 | False | [6 empty] | False |  |  |  | To Do
GANTT_projet (seconde version) | James Fender |  |  | Open | Réaliser un diagramme d'exigences | 2023-02-17 | 2023-02-20 | 2 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False |  | 12 | False | [6 empty] | False |  |  |  | To Do